## Migration Activities
Upgrade Process
Action Id | Action | Owner | Done | Planned |  |  | Actual |  |  | Backup | Comment
|  |  |  | Start Time | End Time | Duration | Start Time | End Time | Duration
Shutdown Systems
SS-0 | Shutdown IIS Services on AWS | Paul | Complete | 0.70833 | 1.125 | 0.41667 | 0.71736 | 0.72431 | 0.0069444
SS-0.1 | Update Slack Channel | Chris | Complete | 44887.9167 | 44887.9236 | 0.0069444 | 0.91944 | 0.91944 | 0
SS-1 | Disable Cube (scheduled jobs) - GS2 | Kaz | Complete | 44887.9167 | 44887.9236 | 0.0069444 | 0.91667 | 0.91667 | 0
SS-2 | Disable new requestes on HAProxy - GS2 | Kaz | Complete | 44887.9236 | 44887.9271 | 0.0034722 | 0.91667 | 0.91875 | 0.0020833
SS-3 | Validate holding page is shown | Kaz | Complete | 44887.9271 | 44887.9306 | 0.0034722 | 0.91875 | 0.91875 | 0 |  | maintenance.warc.com was on the internal dns only; so had to setup an external CName dns record on route53
SS-4 | Shutdown DC Webservers (stop IIS) - GS2 | Kaz | Complete | 44887.9271 | 44887.9479 | 0.020833 | 0.91875 | 0.92708 | 0.0083333
SS-5 | Disable Scheduled jobs on DC GTP Server - GS2 | Kaz | Complete | 44887.9479 | 44887.9688 | 0.020833 | 0.92708 | 0.93542 | 0.0083333
SS-6 | Disable China Scheduled jobs on GTP Server - AliCloud | Kaz | Complete | 44887.9479 | 44887.9688 | 0.020833 | 0.92986 | 0.93542 | 0.0055556 |  | Jake to provide instructions on how to disable via folder move
SS-7 | Shutdown DC GTP Server (whole machine) - GS2 | Kaz | Complete | 44887.9688 | 44887.9896 | 0.020833 | 0.93542 | 0.93611 | 0.00069444 |  | Jake to provide instructions on how to disable via folder move
SS-8 | Shutdown China GTP Server (whole machine) - AliCloud | Kaz | Complete | 44887.9688 | 44887.9896 | 0.020833 | 0.93542 | 0.93611 | 0.00069444
0
| DB Backup & Restore | [7 empty] | 0
BR-1 | Main DB Backup & Restore | Kaz | Complete | 44887.9896 | 44888.1979 | 0.20833 | 0.93611 | 0.375 | -0.56111
BR-2 | Cube DB Backup & Restore | Kaz | Complete | 44887.9896 | 44888.1979 | 0.20833 | 0.93611 | 0.083333 | -0.85278
BR-3 | Copy Filesystem Data | <Automatic every 1 hour> | Complete | 44887.9896 | 44888.1979 | 0.20833 | 0.70833 | 0.09375 | -0.61458 |  | Total Copied Skipped Mismatch FAILED Extras Dirs : 124 124 0 0 0 0 Files : 35233 35233 0 0 0 0 Bytes : 1.299 t 1.299 t 0 0 0 0 Times : 12:58:19 12:58:09 0:00:00 0:00:09
Migration Process Part 1
MO-0 | Update Slack Channel | Chris | Complete | 44891.375 | 44891.3819 | 0.0069444 | 0.375 | 0.375 | 0
MO-0.1 | Restart IIS servers is AWS | Paul | Complete | 44891.375 | 44891.3854 | 0.010417 | 0.375 | 0.37847 | 0.0034722
MO-1 | Change internal DNS for sites | Paul | Complete | 44891.375 | 44891.3958 | 0.020833 | 0.40625 | 0.42292 | 0.016667
MO-1.1 | Release all config changes to reflect migrate.warc.com to www.warc.com (see Comments) | Andy | Complete | 44891.375 | 44891.7604 | 0.38542 | 0.37917 | 9:53 | 0.032639 |  | Build and deploy features/awsmigratetoprod branches from repos below in new AWS TeamCity server http://frawln1papp32/project/_Root?mode=builds Website: https://github.com/ascential/Warc_Warc.com/pull/646 ContentApi: https://github.com/ascential/Warc_ContentAPI/pull/65 SearchApi: https://github.com/ascential/Warc_SearchApi/pull/76 GTP: https://github.com/ascential/WarcTaskProcessing/pull/214 WACS: https://github.com/ascential/Warc_WACS/pull/108 EmailUpdates: https://github.com/ascential/Warc_EmailUpdates/pull/67 WarcPlusManager: https://github.com/ascential/Warc_WarcPlusManager/pull/91 NewCMS: https://github.com/ascential/Warc_NewCms/pull/151 ContentApi deployed - 09:13 EmailUpdates deployed - 09:15 GTP deployed - 09:16 CMS deployed - 09:23 NewExpenditureReport - no deployment required salesforceapi - no deployment required SearchApi deployed - 09:32 WACS deployed - 09:36 WarcPlusManager deploying - 09:41 Website deploying - 09:50 Services.warc.com needed changes manually (Paul @10:16) Gunnreport needed changes manually (Paul @10:18)
MO-2 | Copy latest Docker Images to their own ECR AWS environment / account | Seb | Complete | 44891.375 | 44891.4167 | 0.041667 | 0.375 | 0.37917 | 0.0041667
MO-3 | Remove AWS ECR share policy from Development account | Seb | Complete | 44891.4167 | 44891.4201 | 0.0034722 | 0.37917 | 0.38889 | 0.0097222
MO-4 | Replace K8s manifest files for each repository pipeline to point to their ECR repository | Seb <prepped the previous day> | Complete | 44891.4201 | 44891.441 | 0.020833 | 0.37917 | 0.38889 | 0.0097222 |  | https://github.com/ascential/warc-admin/pull/4 https://github.com/ascential/warc-digitalCommerce-api/pull/2 https://github.com/ascential/warc-gtp-api/pull/6 https://github.com/ascential/warc-identity-server/pull/3 https://github.com/ascential/warc-RankingsAPI/pull/8 https://github.com/ascential/warc-security-api/pull/27 PRs all approved by Jake at 09:32
MO-5 | Resync Postgress DB via DMS | Seb | Complete | 44891.441 | 44891.4549 | 0.013889 | 0.37917 | 0.38889 | 0.0097222
MO-6 | Elastic Search update process | Jake | Complete | 44891.375 | 44891.4167 | 0.041667 | 0.38125 | 0.41736 | 0.036111 |  | Process kicked off at 09:16, worry about the GTP restart at the same time. So started again at 09:28
MO-7 | Update the 4 stored procedures in Cube AWS | Andy | Complete | 44891.375 | 44891.3958 | 0.020833 | 0.425 | 10:39 | 0.01875 |  | Link server reporting some tables not available. New user lost permissions after DB import
0
| Migration Process Part 2 | [7 empty] | 0
MT-1 | Start AWS Cube processes | Theo/ Jake | Complete | 0.45833 | 0.46875 | 0.010417 | 0.44444 | 0.44444 | 0
MT-2 | Start AWS GTP processes | Jake | Complete | 0.46875 | 0.48958 | 0.020833 | 0.42847 | 0.43056 | 0.0020833 |  | Moved from Paul to Jake
MT-3 | Restart China GTP Server | Theo/ Jake | Complete | 0.48958 | 0.51042 | 0.020833 | 0.43264 | 0.43472 | 0.0020833 |  | Jacob Healey can you please provide a list of processes here, or will Kaz know now this has been chenged from Paul doing it?
Basic Test
BT-1 | Monitor any GTP process backlog | Trevor | Complete | 0.51042 | 0.53125 | 0.020833 | 0.4375 | 0.75 | 0.3125
BT-2 | Basic warc.com & www.warc.com site load | Jake & Chris | Complete | 0.51042 | 0.52083 | 0.010417 | 0.44792 | 0.45 | 0.0020833
BT-3 | Basic search check | Jake | Complete | 0.52083 | 0.53125 | 0.010417 | 0.44792 | 0.45 | 0.0020833
BT-4 | Go/ No Go | Chris | Complete | 0.53125 | 0.53125 | 0 | 0.44792 | 0.57153 | 0.12361 |  | Waiting for Cube job to finish Also, may need to test the failover later than expected as the sync is still running Checking what is using the CPU at the moment (100%) Also, deciding if we need to rebuild indexes or not. There may have been a job on the old server which needs migrating across? Doing a reindex Increasing DB server from xl to 2.xl (4x CPU and 32GB RAM to 8x CPU and 64GB RAM) at 12:38 Second server started at 12:47, completed 12:55 Increased IOPS on the DB ES2 from 3,000 to 6,000 and bandwidth from 125 to 300 at 14:47 Added WARCSecurity.dbo.UserData added Index RequireProfileUpdate
Smoke Testing - 1
SO-1 | WACS | All WARC | Complete | 0.53125 | 0.54514 | 0.013889 |  |  | 0
SO-2 | GTP | All WARC | Complete | 0.54514 | 0.55903 | 0.013889 |  |  | 0
SO-3 | Search API | All WARC | Complete | 0.55903 | 0.57986 | 0.020833 | 0.51181 |  | -0.51181
SO-4 | Content API | All WARC | Complete | 0.57986 | 0.59722 | 0.017361 |  |  | 0
SO-5 | SalesForceWebAPI + Additional | All WARC | Complete | 0.59722 | 0.63889 | 0.041667 | 0.55764 | 0.60208 | 0.044444
SO-6 | WARCPlusAdmin | All WARC | Complete | 0.63889 | 0.64583 | 0.0069444 |  |  | 0
SO-7 | Marketo | All WARC | Complete | 0.64583 | 0.65972 | 0.013889 | 0.54167 | 0.65833 | 0.11667 |  |  | :
SO-8 | Email Updates | All WARC | Complete | 0.65972 | 0.67361 | 0.013889 |  |  | 0
SO-9 | UI Smoke testing Scenarios | All WARC | Complete | 0.64583 | 0.77083 | 0.125 |  |  | 0
SO-10 | CMS | All WARC | Complete
S0-11 | www.cmogrowthcouncil.net, www.gunnreport.com basic test | All WARC | Complete | 0.64583 | 0.65625 | 0.010417 | 0.79861 |  | -0.79861 |  | https://receiver.warc.com was on external dns; so we removed it as the landing pagei is a generic ASP.net landing page
S0-12 | Shutdown DB Node 1 - 20% of testing progress | Kaz | Skipped | 0.68194 | 0.69236 | 0.010417 |  |  | 0 |  | To be reviewed w/c 28/11
SO-13 | Restore DB Node 1 - 40% of testing progress | Kaz | Skipped | 0.70417 | 0.71458 | 0.010417 |  |  | 0 |  | To be reviewed w/c 28/11
SO-14 | Shutdown DB Node 2 - 60% of testing progress (once it has sync'd fully with DB node 1) | Kaz | Skipped | 0.72639 | 0.73681 | 0.010417 |  |  | 0 |  | To be reviewed w/c 28/11
SO-15 | Restore DB Node 2 - 80% of testing progress | Kaz | Skipped | 0.74861 | 0.75903 | 0.010417 |  |  | 0 |  | To be reviewed w/c 28/11
SO-16 | Validate all nodes are up to date and sync'd | Kaz | Skipped | 0.77083 | 0.77778 | 0.0069444 |  |  | 0 |  | To be reviewed w/c 28/11
Go Live
GL-1 | Modify external DNS | Paul | Complete | 0.77778 | 0.79167 | 0.013889 | 0.79514 | 0.8 | 0.0048611
GL-2 | Create NewRelic restart on API usage scrips | Paul | Complete | 0.79167 | 0.80556 | 0.013889 |  |  | 0 |  | Done - will confirm they will run later
Smoke Testing - 2
ST-1 | UI Smoke testing Scenarios (reduced) - Using phone or remote VMs | All WARC | Complete | 0.79167 | 0.8125 | 0.020833 | 0.8 | 0.81528 | 0.015278
Go/ No Go
GG-1 | Go/ No Go | Chris | Complete | 0.8125 | 0.82292 | 0.010417 | 0.82153 | 0.82153 | 0 |  | GO
GG-2 | Update Slack Channel | Chris | Complete | 0.82292 | 0.82986 | 0.0069444 | 0.82292 | 0.82292 | 0
GG-3 | Send WhatsApp to John C | Chris | Complete | 0.82986 | 0.83333 | 0.0034722 | 0.83333 | 0.83333 | 0
|  | Rollback Start Time |  | 2022-11-27 17:00
Rollback Process
Action Id | Action | Owner |  | Planned |  |  | Actual |  |  | Backup | Comment
|  |  |  | Start Time | End Time | Duration | Start Time | End Time | Duration
Shutdown Systems
RR-SS-1 | If external DNS is pointing to AWS, move back to DC | Paul |  | 44892.7083 | 44892.7222 | 0.013889 |  |  | 0
RR-SS-2 | Change internal DNS for sites | Paul |  | 44892.7083 | 44892.7188 | 0.010417 |  |  | 0
RR-SS-3 | Shutdown AWS GTP Server (whole machine) | Kaz |  | 44892.7083 | 44892.7118 | 0.0034722 |  |  | 0
RR-SS-4 | Shutdown China GTP Server (whole machine) | Kaz |  | 44892.7118 | 44892.7222 | 0.010417 |  |  | 0
RR-SS-5 | Disable AWS Cube (scheduled jobs) | Kaz |  | 44892.7222 | 44892.7292 | 0.0069444 |  |  | 0
Re-enable DC
RR-RE-1 | Replace K8S configs (via Team City?) | Seb |  | 44892.7292 | 44892.7708 | 0.041667 |  |  | 0
RR-RE-2 | Start DC Cube processes | Kaz |  | 44892.7292 | 44892.7396 | 0.010417 |  |  | 0
RR-RE-3 | Start DC Webservers (start IIS) | Paul |  | 44892.7292 | 44892.75 | 0.020833 |  |  | 0
RR-RE-4 | Start DC GTP UK processes | Jake |  | 44892.7396 | 44892.7604 | 0.020833 |  |  | 0
RR-RE-5 | Restart China GTP Server | Paul |  | 44892.7604 | 44892.7812 | 0.020833 |  |  | 0
RR-RE-6 | Monitor any GTP process backlog | Jake |  | 44892.7812 | 44892.8021 | 0.020833 |  |  | 0
Basic Test
RR-BT-1 | Basic warc.com & www.warc.com site load | Jake |  | 44892.8021 | 44892.8125 | 0.010417 |  |  | 0
RR-BT-2 | Basic search check | Jake |  | 44892.8125 | 44892.8229 | 0.010417 |  |  | 0
RR-BT-3 | Go/ No Go | Chris |  | 44892.8229 | 44892.8229 | 0 |  |  | 0
Smoke Testing
RR-ST-1 | WACS |  |  | 44892.8229 | 44892.8368 | 0.013889 |  |  | 0
RR-ST-2 | GTP |  |  | 44892.8229 | 44892.8368 | 0.013889 |  |  | 0
RR-ST-3 | Search API |  |  | 44892.8229 | 44892.8438 | 0.020833 |  |  | 0
RR-ST-4 | Content API |  |  | 44892.8229 | 44892.8403 | 0.017361 |  |  | 0
RR-ST-5 | SalesForceWebAPI + Additional | Jaime |  | 44892.8229 | 44892.8646 | 0.041667 |  |  | 0
RR-ST-6 | WARCPlusAdmin |  |  | 44892.8229 | 44892.8299 | 0.0069444 |  |  | 0
RR-ST-7 | Marketo |  |  | 44892.8229 | 44892.8368 | 0.013889 |  |  | 0
RR-ST-8 | Email Updates |  |  | 44892.8229 | 44892.8368 | 0.013889 |  |  | 0
RR-ST-9 | UI Smoke testing Scenarios |  |  | 44892.8229 | 44892.9479 | 0.125 |  |  | 0
Contingency
RR-CO-1 | Contingency |  |  | 44892.9479 | 44892.9896 | 0.041667 |  |  | 0
Go/ No Go
RR-GG-1 | Go/ No Go |  |  | 44892.9896 | 44892.9965 | 0.0069444 |  |  | 0

## DNS
Internet Facing | Current DNS | Current TTL | New DNS
www.warc.com | d3tm9upglshe8e.cloudfront.net. |  | a0cb9acd2b9ac330f.awsglobalaccelerator.com.
dig.warc.com | lba.hosting-ascential.com. |  | a0cb9acd2b9ac330f.awsglobalaccelerator.com.
expenditurereport.warc.com | lba.hosting-ascential.com. |  | a0cb9acd2b9ac330f.awsglobalaccelerator.com.
salesforce.warc.com | lba.hosting-ascential.com. |  | a0cb9acd2b9ac330f.awsglobalaccelerator.com.
openathens.warc.com | lba.hosting-ascential.com. |  | a0cb9acd2b9ac330f.awsglobalaccelerator.com.
receiver.warc.com | lba.hosting-ascential.com. | <removed from external DNS> | a0cb9acd2b9ac330f.awsglobalaccelerator.com.
resource.warc.com | lba.hosting-ascential.com. |  | a0cb9acd2b9ac330f.awsglobalaccelerator.com.
cdn.warc.com |  |  | a0cb9acd2b9ac330f.awsglobalaccelerator.com.
VPN Access Only
cmsservice.warc.com | 10.203.2.33 |  | frawln1papp31.trgfrnt.com.
warcplusadmin.warc.com | lba.hosting-ascential.com. |  | internal-webfarmmaininternal-1371301216.eu-west-2.elb.amazonaws.com.
services.warc.com | lba.hosting-ascential.com. |  | internal-webfarmmaininternal-1371301216.eu-west-2.elb.amazonaws.com.
new-admin.warc.com | lba.hosting-ascential.com. |  | internal-webfarmmaininternal-1371301216.eu-west-2.elb.amazonaws.com.
warcsearchapi-internal.warc.com | internal-webfarmmaininternal-1371301216.eu-west-2.elb.amazonaws.com. |  | internal-webfarmmaininternal-1371301216.eu-west-2.elb.amazonaws.com.
contentapi-internal.warc.com | internal-webfarmmaininternal-1371301216.eu-west-2.elb.amazonaws.com. |  | internal-webfarmmaininternal-1371301216.eu-west-2.elb.amazonaws.com.
authorisation.warc.com | lba.hosting-ascential.com. |  | internal-webfarmmaininternal-1371301216.eu-west-2.elb.amazonaws.com.
admin.warc.com | hsln1lba01.trghosting.net. |  | internal-webfarmmaininternal-1371301216.eu-west-2.elb.amazonaws.com.
newcms.warc.com | lba.hosting-ascential.com. |  | internal-webfarmmaininternal-1371301216.eu-west-2.elb.amazonaws.com.
warcsearchingestor.warc.com |  |  | internal-webfarmmaininternal-1371301216.eu-west-2.elb.amazonaws.com.
warcsearchapi.warc.com | lba.hosting-ascential.com. |  | internal-webfarmmaininternal-1371301216.eu-west-2.elb.amazonaws.com.
contentapi.warc.com | lba.hosting-ascential.com. |  | internal-webfarmmaininternal-1371301216.eu-west-2.elb.amazonaws.com.

## PreMigration Tasks
Pre-Migration Actions
Action | Name | When (if timed) | Complete? | Comment
Migrate IIS config fo Redirect service | Paul | n/a | n/a | Compression issue fixed, no more actions. All remain on the IIS
Set TTL on external DNS recrods to 5m | Paul | 2022-11-24 |  | Planned on the Thur 24/11
Slack and email to all internal WARC staff | Chris/ Elias | 2022-11-14 | Complete
Emails to customers (Week before) | Elias | 2022-11-18 | Complete
Emails to US cusomers (Wed morning UK time) | Elias | 2022-11-23 | Complete
Contact Facilities about team on site (Wed) | Elias | 2022-11-23 | Complete (24/11)
Emails to remaining customers (Fri morning UK time) | Elias | 2022-11-25
Slack and email to all internal WARC staff | Chris/ Elias | 2022-11-23 | Complete
Slack and email to all internal WARC staff | Chris/ Elias | 2022-11-25 | Complete
Jake and Seb to have a call to build K8s | Jake/ Seb |  |  | Will there be any commits 2 or less days before. Will clone the repo's and change the pipelines. Work will be on by Sebin a PR for Jake to approve
Change web configs from migrate.warc.com to warc.com | Andy | 2022-11-23 | Complete, PRs ready | PR by COP Thursday; work to be done well in advance
Change config on IIS bindings from migrate.warc.com to warc.com | Paul | 2022-11-24 | Complete | By COP Thursday
Provide times to the team on when they are expected to start | Chris | 2022-11-24 | Complete | By COP Thursday
Clarification Required
Action | Name |  | Complete? | Comment
Do we need to shutdown China? | Chris |  |  | No
Video process, and where they are stored in China | Jake |  |  | Local drive in China
Prevent Salesforce from updating from Friday afternoon | Errol
Talk to "Love The Work about Salesforce | Lions - Nicola?
Check with Hannah what Salesforce scheduled jobs run | Hannah |  |  | Email sent to Hannah 03/11 @12:08
Actions post migration
Remove this, and create the same using migrations CREATE INDEX [AfterMigrate_RequireProfileUpdate] ON [WARCSecurity].[dbo].[UserData] ([RequireProfileUpdate]) WITH (FILLFACTOR=100, ONLINE=ON, SORT_IN_TEMPDB=OFF, DATA_COMPRESSION=NONE); CREATE INDEX [IsWarcInChina_DateLastUpdated_Includes] ON [WARCSecurity].[dbo].[CompanyAccount] ([IsWarcInChina], [DateLastUpdated]) INCLUDE ([DateCreated]) WITH (FILLFACTOR=100, ONLINE=ON, SORT_IN_TEMPDB=OFF, DATA_COMPRESSION=NONE); | Chris |  |  | Create a ticket for this
Create an update all DB Stats & Indexes job daily | Kaz

## Contacts
Contacts
First Name | Last Name | Phone Number (do not share) | Location | Role | On Call | Escalation Point | Communicate Start | Communicate Updates | Communicate End
Chris | Loader | 07307 612461 | Kingsway | On site coordinator, Sponsor | Active during project | Yes - Level 1 | Yes | Yes | Yes
Deborah | Fisayo |  | Home | Tester | Active during project | No | Yes | Yes | Yes
Jacob | Healey |  | Kingsway | Developer, Lead Engineer | Active during project | No | Yes | Yes | Yes
Jaime | DifoLorenzo |  | Home | Tester, Salesforce super user | Active during project | No | Yes | Yes | Yes
Kaushik | Chhaya | 7734967347 | Home | Infrastructure DB | Active during project | No | Yes | Yes | Yes
Paul | Seward |  | Kingsway | Infrastructure | Active during project | No | Yes | Yes | Yes
Seb | Gogoasa |  | Kingsway | Infrastructure K8S | Active during project | No | Yes | Yes | Yes
Theo | Arulakshman |  | Home | Infrastructure | Active during project | No | Yes | Yes | Yes
Trevor | Stephenson |  | Kingsway | Developer | Active during project | No | Yes | Yes | Yes
Andrew | Lam |  | Home | Developer | Yes | No | Yes | Yes | Yes
John | Cocklin |  | Remote | Developer | Yes (Sunday) | No | Yes | Yes | Yes
Simon | Morgan |  | n/a | Head of Security | No | No | Yes | Exceptional Only | Yes
Stuart | McKay |  | n/a | Head of Cloud Governance | No | No | Yes | Exceptional Only | Yes
Dan | Fogarty |  | n/a | Project Manager | No | Yes - Level 2 | Yes | Yes | Yes
John | Callero | 07802933223 | n/a | Head of Platforms | No | Yes - Level 2 | Yes | Yes | Yes
Paul | Shannon |  | n/a | Project Manager | No | Yes - Level 2 | Yes | Yes | Yes
Hiran | Pattani | 07921501696 | n/a | CTO | No | Yes - Level 3 | Yes | Exceptional Only | Yes
Lee | Freeman |  | n/a | VP Technology | No | Yes - Level 3 | Yes | Exceptional Only | Yes
Samuel | Covert |  | n/a | VP Data Science | No | Yes - Level 3 | Yes | Exceptional Only | Yes
Paul | Coxhill |  | n/a | WARC CEO | No | Yes - Level 4 | Yes | Exceptional Only | Yes
Sean | Harley |  | n/a | CIO | No | Yes - Level 5 | Yes | Exceptional Only | Yes
Barbara | Kuhr |  | n/a | VP Brand | No | No | Yes | Exceptional Only | Yes
Carolyn | Murphy |  | n/a | VP Americas | No | No | Yes | Exceptional Only | Yes
David | Tiltman |  | n/a | SVP Content | No | No | Yes | Exceptional Only | Yes
Ed | Pank |  | n/a | VP APAC & Advisory | No | No | Yes | Exceptional Only | Yes
Errol | Baran |  | n/a | VP Commercial | No | No | Yes | Exceptional Only | Yes
Francis | Wong |  | n/a | VP & Chief Experience Officer | No | No | Yes | Exceptional Only | Yes
Michael | Ossei |  | n/a | Director Product | No | No | Yes | Exceptional Only | Yes
Amin | Mrini |  | n/a | VP Business Operations | No | No | Yes | Exceptional Only | Yes
Hannah | Lever |  | n/a | Salesforce | No | No | Yes | Exceptional Only | Yes
Neil | Robertson-Ravo |  | n/a | Director Data Platforms | No | No | Yes | Exceptional Only | Yes
Chris | Ward |  | n/a | Lions Developer (interested in Salesforce) | No | No | Yes | Exceptional Only | Yes
Marc | Trepanier |  | n/a | Lions Developer (interested in Salesforce) | No | No | Yes | Exceptional Only | Yes

## Constants
Migration Start Time | 2022-11-22 22:00
Saturday Start Time | 2022-11-26 09:00